Trimestral progress report 1

FAR-SIDS. Foreign Aid, Remittances, and Wellbeing in Small Island Developing States

| Grant agreement | 101244526, HORIZON-TMA-MSCA-PF-EF, call HORIZON-WIDERA-2024-TALENTS-02 |
| --- | --- |
| Deliverable | D.1.3, the first of eight quarterly reports, with the quarterly review of the career development plan |
| Reporting period | 15 June to 15 September 2026 |
| Fellow | Dr Roxane de Waegh, MSCA Postdoctoral Fellow, Institute for Islands and Small States (ISSI), University of Malta |
| Supervisor | Professor Stefano Moncada, Director, ISSI |
| Date | 15 September 2026 |

1. Where the project stands

The first quarter prepared the ground for the fieldwork of April 2027: the evidence base, the survey, the ethics applications and the partnerships that fieldwork depends on.

Systematic review closed. 201 studies included on 12 August after two search arms; the protocol, flow diagram and theme map are published on the project website. This is the evidence base for paper one and the DevNet presentation.

Household survey written. Six blocks in three country forms, each question matched to the national household survey the country already runs. The French version for the Comoros exists; the Tongan and Shikomori translations still need to be done with local research partners before the pilot.

Two ethics applications submitted. University of Malta on 28 August, and The University of the West Indies, Mona, on 7 September for its committee meeting of 2 October.

Jamaica’s national household survey received. We submitted a request to Richard Leach, person in charge of the Derek Gordon Databank at SALISES, to receive data on aid and remittance receipts in Jamaica. On 28 August, we received the data. SALISES released 12 years of the Survey of Living Conditions, 2009 to 2023, at household level. Jamaica’s published poverty rate was recalculated from the files and matched in ten of the twelve years. The data support a second paper, written with SALISES, before any fieldwork begins.

Conferences and seminars. The DevNet 2026 abstract was accepted on 7 September, an abstract was submitted to ISISA Curaçao 2027 the same day, and FAR-SIDS was presented to the RESI week cohort on 8 September.

2. Year 1 deliverables on 15 September

| Code | Deliverable | Status | Where it stands |
| --- | --- | --- | --- |
| D.1.1 | Mobility declaration, career plan, training plan | Done, 24 June | Declaration validated on the Portal; plan signed by myself and supervisor |
| D.1.2 | Data management plan and digital platform | Under way | Website live since June; plan revised with the Open Science office on 1 July and again on 26 August. The Zenodo and drUM deposits have to be in place before the December check |
| D.1.4 | Trimestral progress report 2 | 15 December | Written from this layout, with the second quarterly review of the career development plan |
| M.1.1 | Milestone: plans and platform complete | 14 December | Career plan, data management plan and website; the signed career plan is uploaded to the Funding and Tenders Portal |
| D.2.1 | Quantitative methods training | Done, 24 July | IBM SPSS Introduction and Intermediate; two certificates |
| D.2.2 | Policy writing training | December | UNU-MERIT policy brief writing course |
| D.2.3 | Leadership and project management | October | A leadership unit (DOC6009 or DOC6058) and DOC6068 Project Management, Doctoral School units enrolled when the catalogue opens |
| D.2.4 | Integrated methods training | Under way | HarvardX Statistics and R, finished in October |
| D.2.5 | FinTech elective | Done, 17 August | Inter-American Development Bank course; certificate and badge filed. The reimbursement claim is with Finance for approval |
| Training | Other courses completed this quarter | Done | Commonwealth Climate Finance Essentials, 3 September, and IMF Financial Programming and Policies Part 1, 6 September; both certificates filed and published |
| D.2.6 | Teaching seminar 1, ISSI Master’s | October | NVivo module in ISS5220 Research Methodology, 7 and 14 October; seminar in ISS5200 Economic and Environmental Issues, 20 and 21 October |
| D.2.7 | Teaching seminar 2, Hildesheim | 27 November | Designed with Dr Schmitz; online, ninety minutes |
| D.2.8 | MOOC 1, Bridging Cultures with Reciprocity | Not started | Outline in October, recording in January |
| D.3.1 | Language practice, Tongan and Shikomori | Under way | Practice is happening but is not logged, so a simple record of dates and minutes is needed as evidence before milestone M.3.2 in March 2027 |
| D.3.2 | Partnerships with the partner universities | Under way | Contacts in all three countries; no memorandum of understanding signed |
| D.3.3 | Study sites and community stakeholders | Not selected | Aim: six communities of fifty households per country. Jamaica starts from the Social Development Commission and UNDP community profiles, on Dr Dietrich Jones’s advice. The request for quotes to survey providers and the fieldwork agreements and letters were written on 2 September |
| M.3.1 | Milestone: launch the project social media | March 2027 | Building now: one visual story and one listening note per country each week since 1 August, published on the website |
| D.5.1 | Gender sensitive monitoring framework | Draft version | 20 of 39 indicators address gender (51 per cent, 50 required); Final version will be complete after key stakeholder consultations with women’s group and the twenty household pilot in each country, at month 16 |
| M.5.1 | Milestone: review of World Bank and OECD data | Under way | National panel for the three countries assembled; documented dataset in November |
| D.6.5 | Conference 1, DevNet 2026 | Accepted | Paper at draft six; Wellington, 2 to 4 December |
| D.7.5 | Journal article 1, the systematic review | Under way | The review is closed, so the paper is submitted by 27 November 2026, well ahead of its March 2028 date |
| Ethics | Malta, Jamaica, Tonga, Comoros | Two submitted | Malta 28 August; Jamaica 7 September. Feedback from both is expected in October; Tonga and the Comoros follow the partner university introductions |

Codes follow the grant agreement: D is a deliverable and M a milestone, and the first number is the work package (WP), so D.5.1 is the first deliverable of Work Package 5. DOC and ISS codes are University of Malta study units. The Year 1 deliverables whose work begins after this quarter are not listed here, and none has begun: D.1.5, D.1.6, D.3.4, M.2.1, M.3.2, D.4.1, D.4.2, D.4.4, D.6.1, D.6.2 and D.7.1.

3. Changes to the plan, each with its reason

| Item | Planned | Done instead | Reason |
| --- | --- | --- | --- |
| D.2.1 Quantitative methods training | DOC6021 Quantitative Research Methods and DOC6067 Using R for Data Processing, Doctoral School | Two SPSS courses, July | They ran in July and cover the statistical base the project needs, and they were recorded on 16 August 2026 as closing the deliverable |
| D.2.2 Policy writing training | DOC6047, the Doctoral School policy writing unit | UNU-MERIT policy brief writing course, December | DOC6047 is no longer offered; the career development plan already names UNU-MERIT as the supporting resource |
| D.2.4 Integrated methods training | ISS5220 Research Methodology | HarvardX Statistics and R | Since I am now teaching the NVivo module of ISS5220 under D.2.6, the unit cannot also count as my training |
| Survey design training | World Bank course on multi-topic household surveys | Audit of the survey against Grosh and Glewwe | The course was dormant when the survey was written; the audit uses the book the course is built on |
| D.5.1 Gender sensitive monitoring framework | July 2026 | 2 September 2026 | Rebuilt on the survey actually submitted to the ethics committees rather than on an earlier draft. The Gantt places this in July 2026 and the Objective 2 indicator at month 16, October 2027, so version 0.2 sits between them and version 1.0 follows the pilots |
| D.6.5 Conference 1 | December 2027 in the Gantt half year table | December 2026 | The deliverable glossary names DevNet 2026 as conference 1, and the abstract is accepted, so the conference paper is delivered a year before its Gantt column |
| D.2.6 Teaching seminar 1 | One 90 minute session in the ISSI Master’s | Two modules, four sessions in October | The NVivo module in ISS5220 was added when the previous lecturer left, so the teaching is four sessions rather than one |

4. The quarter ahead, to 15 December 2026

| What happens | Oct | Nov | Dec | Deliverable |
| --- | --- | --- | --- | --- |
| Semester one opens; leadership unit and DOC6068 enrolled; HarvardX finished | ● |  |  | D.2.3 leadership training; D.2.4 integrated methods training |
| Mona ethics committee meets 2 October; its decision follows at least two weeks later | ● |  |  | Ethics |
| Malta ethics feedback due within 30 working days (about 13 October); application revised in October | ● |  |  | Ethics |
| NVivo module taught 7 and 14 October; ISS5200 seminar taught 20 and 21 October | ● |  |  | D.2.6 teaching seminar 1 |
| Malta: revised application to the University data protection committee by 2 November (or 27 November for December) |  | ● |  | Ethics |
| DevNet registration and flights bought through procurement before 3 November | ● | ● |  | D.6.5 DevNet conference |
| Jamaica: revised application resubmitted by 9 November for the Mona meeting of 4 December |  | ● |  | Ethics |
| Both papers submitted by 27 November, before the flight to Wellington |  | ● |  | D.7.5 journal article 1; WP7 dissemination |
| Hildesheim guest seminar, 27 November |  | ● |  | D.2.7 teaching seminar 2 |
| Paper one presented at DevNet 2026, Wellington, 2 to 4 December |  |  | ● | D.6.5 DevNet conference |
| UNU-MERIT policy brief writing course |  |  | ● | D.2.2 policy writing training |
| Data management plan checked and career plan uploaded by 14 December; report 2 on 15 December |  |  | ● | M.1.1 first milestone; D.1.4 report 2 |

Tonga and the Comoros go through the same steps once the introductions to Tonga National University and the Université des Comores are made: submission to the partner university, feedback, revision and resubmission before the first fieldwork in each country.

5. Two papers submitted before DevNet

Both papers are submitted by 27 November 2026, before the flight to Wellington. Professor Moncada’s guidance on 2 September was to aim highest first, so each paper goes to the highest ranked journal that fits it and moves down the list only if that journal declines. The lists below were settled on 11 September. All six are published by Elsevier, Taylor & Francis or Wiley, which each hold a read and publish agreement with the University of Malta, so open access should cost the project nothing.

| Paper | First choice | Second | Third |
| --- | --- | --- | --- |
| Paper 1, the PRISMA systematic review | World Development (Elsevier) | Journal of Development Effectiveness (Taylor & Francis) | Development Policy Review (Wiley) |
| The Jamaica paper, with SALISES | Journal of Development Studies (Taylor & Francis) | Population and Development Review (Wiley) | Development and Change (Wiley) |

6. Career development plan review

This report is the first quarterly review of the plan under section 3.6. No change is proposed to the long term objectives in section 2. For agreement with Professor Moncada, section 3.1 records that the review paper and the Jamaica paper are both submitted before DevNet. Section 3.2 records the units actually available: the SPSS courses in place of DOC6021 and DOC6067, the UNU-MERIT course in place of DOC6047, and HarvardX Statistics and R in place of ISS5220. Section 3.5 records that the ISSI teaching under D.2.6 covers two units. The leadership unit and DOC6068 enrol in October.